## Financial Summary Capital
23/24
Expenditure | Area |  | £000 | Invoices paid.
Design Stage | Project Approval | Centrica project initiation costs: Investment Grade Audit, concept design, legal costs, tendering of contractors and suppliers, procurement of key assets | 355 | Balance due.
| Out to tender |  | 269.8425
| Tenders returned |  | 472.4858
| Order Placed |  | 3694.18
| Designs Completed | Conversion of concept design into full proposal with energy performance guarantee | 355.045
| Total |  | 5146.5533
On Site | Insurance | Centrica project enabling costs | 22.26
| Signature of Agreement |  | 163.09
| Welfare Cabins Physically on site | Centrica construction phase costs | 35.55
| Insulation |  | 75.078
| Heat Pumps |  | 9920.542
| Autoclaves |  | 404.45
| HELGA FRAMEWORK | NHS Contract Fee | 49.37
| Contingency |  | 300
| Total |  | 10970.34
Completed on site |  | Site clearance at end of construction | 249.91
Final commissioning |  | Final system checks/testing and monitoring and verification of energy savings guarantee | 464.0108
713.9208
16830.8142
3366.1628
20196.977

## Condensed Schedule
Salix Milestones | Ex Vat | Inc VAT | CBS Milestone | Value | Month
Project Approval | 355000 | 426000 | Project Approval | 355000 | 2023-01-01
Out to tender | 269842.5 | 323811 | Out to tender | 269842.5 | 2023-01-01
Tenders returned | 472485.83 | 566982.996 | Tenders returned | 472485.83 | 2023-04-01
Order Placed | 3694180 | 4433016 | Order Placed for large ticket items | 3694180 | 2023-02-01
Designs Completed | 355045 | 426054 | Detailed Design | 177522.5 | 2023-07-01
|  |  |  | 88761.25 | 2023-09-01
|  |  |  | 88761.25 | 2023-09-01
Works in progress on site | 10970340 | 13164408 | Insurance | 22260 | 2023-07-01
|  |  | Signature of Agreement | 163090 | 2023-07-01
|  |  | Welfare Cabins Physically on site | 35550 | 2023-12-01
|  |  | Insulation | 75078 | 2024-01-01
|  |  | Heat Pumps | 2766585 | 2023-11-01
|  |  |  | 2305487.5 | 2023-12-01
|  |  |  | 2002733.5 | 2024-01-01
|  |  |  | 1504097 | 2024-02-01
|  |  |  | 1341639 | 2024-03-01
|  |  | Autoclaves | 268150 | 2024-01-01
|  |  |  | 68150 | 2024-02-01
|  |  |  | 68150 | 2024-03-01
|  |  | Helga | 49370 | 2023-07-01
|  |  | * Trust Contingency | 250000 | 2023-11-01
|  |  |  | 50000 | 2023-12-01
Completed on site | 249910 | 299892 | Completed on site | 249910 | 2024-12-01
Final commissioning | 464010.84 | 556813.008 | Final commissioning | 154670.28 | 2025-01-01
|  |  |  | 154670.28 | 2025-02-01
|  |  |  | 154670.28 | 2025-03-01
Lifecycle Cost (From Trust | 450000 | 540000 | Lifecycle Cost | 150000 | 2024-04-01
|  |  |  | 150000 | 2024-05-01
|  |  |  | 150000 | 2024-06-01
* Trust contingency will be drawn down from Salix but not paid to Centrica
Total Ex Vat | 17280814.17 |  |  | 17280814.17
VAT @20% | 3456162.834 |  |  | 3456162.834
Total inc VAT | 20736977.004 |  |  | 20736977.004
Funding
IES | 20196977.004
Savings/reduction in costs | 540000 | NB : Via Mercia when the gas boilers do not need lifecycle repayment.
20736977.004
New Revenue Implications
Centrica | 163744 | NB: Maintenance of the energy centre PSDS3 works

## Payment
Wye Valley Phase 2 Salix Payment Schedule
Rev 3 25-05-23
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
Salix Milestones | Ex Vat | Inc VAT | CBS Milestone
Project Approval | 355000 | 426000 | Project Approval | 355000
Out to tender | 269842.5 | 323811 | Out to tender | 269842.5
Tenders returned | 472485.83 | 566982.996 | Tenders returned |  |  |  | 472485.83
Order Placed | 3694180 | 4433016 | Order Placed for large ticket items |  | 3694180
Designs Completed | 355045 | 426054 | Detailed Design | [6 empty] | 177522.5 |  | 177522.5
Works in progress on site | 10620970 | 12745164 | Insurance | [6 empty] | 22260
|  |  | Signature of Agreement | [6 empty] | 163090
|  |  | Welfare Cabins Physically on site | [11 empty] | 35550
|  |  | Loft Insulation | Pathology Install Complete | [12 empty] | 53612
|  |  |  | Materials Delivered | [11 empty] | 4066
|  |  |  | Age Care Install Complete | [12 empty] | 17400
|  |  | Heat Pumps | Procurement of materials for Energy Centre Mechanical Works | [9 empty] | 922195
|  |  |  | Off-Site Fabrication of Energy Centre Skids and Pipework | [10 empty] | 461097.5 | 461097.5
|  |  |  | Procurement of materials for Package Plant Room Mechanical Works | [9 empty] | 922195
|  |  |  | Off-Site Fabrication of Package Plant Room | [9 empty] | 922195
|  |  |  | Procurement of HV Works | [10 empty] | 368878
|  |  |  | Procurement of BMS Works | [10 empty] | 368878
|  |  |  | Procurement of District Heating Works | [10 empty] | 368878
|  |  |  | Procurement of Energy Centre Build | [10 empty] | 368878
|  |  |  | Procurement of Electrical and Controls Package | [10 empty] | 368878
|  |  |  | Site Clearance and Foundations for Energy Centre Build | [11 empty] | 770818
|  |  |  | Deliver District Heating Pipework and Start Installation | [11 empty] | 770818
|  |  |  | Civils for Mortuary Package Plant Room | [12 empty] | 733279
|  |  |  | District Heating Installtion Complete to Pathology | [12 empty] | 770818
|  |  |  | Procurement of M&E Works for Satelite Plant Rooms | [13 empty] | 1341639
|  |  | Autoclaves | Deliver Transformer to Site and Install LV Supplies SSD | [11 empty] | 268150
|  |  |  | Install New Electric Steam Generators in SSD | [12 empty] | 68150
|  |  |  | Procurement of Pathology Electric Steam Generator Works | [13 empty] | 68150
Helga | 49370 | 59244 | Helga | [6 empty] | 49370
Trust Contingency | 300000 | 360000 | Trust Contingency | [10 empty] | 250000 | 50000
Completed on site | 249910 | 299892 | Completed on site | [23 empty] | 249910
Final commissioning | 464010.84 | 556813.008 | Final commissioning | [24 empty] | 154670.28 | 154670.28 | 154670.28
|  |  |  | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | August | September | October | November | December | January | February | March
Centrica Project Value | 16830814.17 | 20196977.004 | Total Ex Vat | 624842.5 | 3694180 | 0 | 472485.83 | 0 | 0 | 412242.5 | 0 | 177522.5 | 0 | 3016585 | 2391037.5 | 2274949.5 | 1643259 | 1409789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249910 | 154670.28 | 154670.28 | 154670.28
|  |  | VAT @20% | 124968.5 | 738836 | 0 | 94497.166 | 0 | 0 | 82448.5 | 0 | 35504.5 | 0 | 603317 | 478207.5 | 454989.9 | 328651.8 | 281957.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49982 | 30934.056 | 30934.056 | 30934.056
Lifecycle Contribution (from Trust, assuming boiler replacement works are undertaken) | 450000 | Assume not Vatable |  | 749811 | 4433016 | 0 | 566982.996 | 0 | 0 | 494691 | 0 | 213027 | 0 | 3619902 | 2869245 | 2729939.4 | 1971910.8 | 1691746.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299892 | 185604.336 | 185604.336 | 185604.336
Salix Grant | 16830814.17 | 20196977.004 |  | 749811 | 4433016 | 0 | 566982.996 | 0 | 0 | 494691 | 0 | 213027 | 0 | 3619902 | 2869245 | 2729939.4 | 1971910.8 | 1691746.8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 299892 | 185604.336 | 185604.336 | 185604.336