## Stage 3 Risk Register
Project: Wye Valley IES
Risk Register 23102023
Pre-mitigation | [11 empty] | Post-mitigation
No. | Title | Risk | Time | Cost | Quality | Safety | Probability | Impact | Likelihood | Owner | Route to Resolve/ Mitigate | Probability | Impact | Likelihood | Review | Date Raised | Date Closed
1 | Pre-con
1 | Trust Governance | Adequate allowances for Trust Governance. | x |  |  |  | 4 | 3 | 12 | WVT
2 | Pre-con | Car parks will need to be closed | x |  |  |  | 5 | 3 | 15 | WVT | Demonstrate extent of closure in time to enable parking options to be considered.
3 | Pre-con | Salix fail to approve CN or reduce the fund | x | x |  |  | 4 | 4 | 16 | WVT | Salix CN issued and closed out
4 | Pre-con | Centrica fail to provide detail to inform the FBC in a timely manner. | x |  |  |  | 4 | 3 | 12 | CBS | Centrica to action
5 | Pre-con | Planning permission denied. | x | x |  |  | 2 | 3 | 6 | WVT/CBS | Maintain on going dialogue with planning authority during determination period.
6 | Planning Determination Period | Determination period is regularly missed by Herefordshire council | x |  |  |  | 3 | 4 | 12 | CBS | Maintain on going dialogue with planning authority during determination period.
7 | Pre-commencement Condition Wording | Wording of pre-commencement conditions proposing restrictions on starting site activities. | x |  |  |  | 3 | 5 | 15 | CBS | Maintain on going dialogue with planning authority during determination period.
8 | Pre-con | Concern/difficulty around managing the project spend and the Trusts CDEL limitations. | x | x |  |  | 3 | 4 | 12 | WVT | Ongoing liaison with finance.
9 | Pre-con | Trust failing to approve cash flow |  |  |  |  | 4 | 4 | 16 | WVT | Finance made aware of requirement - ongoing discussion to satisfy audit.
2 | Construction
2 | Construction | CBS fail to resource the scheme effectively | x |  |  |  | 5 | 3 | 15 | CBS | Ensure detail/documentation is filed correctly and information is circulated to all concerned.
3 | Construction | Long lead times on items | x |  |  |  | 3 | 3 | 9 | CBS | review procurement schedule.
4 | Construction | Site set up/logistics taking up further space on site/large pipe lengths etc. |  |  |  |  | 4 | 4 | 16 | CBS | Site set up detail to be issued for review and comment. Detail received and under review.
5 | Commissioning | No adequate allowance for commissioning in advance of equipment installation. | x |  |  |  | 3 | 4 | 12 | CBS | Early commissioning programme in draft to be issued.
6 | Construction | O&M team not engaged early enough in process to effect seamless transition at PC for PSDS 3 OPEX | x | x | x | x | 3 | 4 | 12 | WVT | Ensure dialogue between all parties
7 | Construction | Salix spend time constraints. | x |  |  |  | 4 | 3 | 12 | CBS | Appraise cash flow and agree monthly spend demonstrating value against application/consider retention value March 24.
8 | Construction | Scope gap | x | x |  |  | 3 | 3 | 9 | CBS | Emit and add as required to maintain nil variance to FPLS.
9 | Construction | Scope creep | x |  |  |  | 3 | 4 | 12 | CBS | not permitted
10 | Construction. | Disruption to access ways and all hospital users | x |  |  | x | 3 | 2 | 6 | CBS | Review RAMS
11 | Pre-con | Clash with adjacent Education Centre Building | x |  |  |  | 3 | 3 | 9 | CBS | Share detail with Architype.
12 | Construction | Resilience solution unknown. | x | x |  |  | 4 | 4 | 16 | CBS | Cost options for review and incorporate into FBC
13 | Construction | Archaeological issues cause delays. | x |  |  |  | 3 | 4 | 12 | CBS | Meeting held with J Cotton archaeological advisor to the planners 031023 with site visit scheduled for 041023 to determine trial holes/excavation areas undertaken during planning determination period. Revised quote from Headland due w/c 23/10/2023.
14 | Construction | Bodies could potentially be discovered during archaeological works | x |  |  |  | 3 | 4 | 12 | CBS | as above
15 | Construction | Discovery of unknown contamination (hydrocarbon, asbestos, arsenic etc.) as works proceed, and subsequent management. | x |  |  |  | 3 | 4 | 12 | CBS | as above
16 | Construction | Ground Investigation - failure to take account of surveys | x |  |  |  | 3 | 4 | 12 | CBS | review all available detail and determine if further investigation is considered necessary
17 |  | potential damage to party walls and third party property caused by the works’ | [6 empty] | 0
18 | Construction | Large new plant rooms required near mortuary. | x |  |  |  | 3 | 3 | 9 | CBS | Location agreed item closed.
19 | Construction | Key staff member leave their respective employer |  |  |  |  | 3 | 4 | 12 | ALL | Ensure detail/documentation is filed correctly and information is circulated to all concerned.
20 | Construction | Establishing all cost savings when considering boiler removal including cost reduction for risk liability. |  | x |  |  | 3 | 4 | 12 | ALL | Early discussion - consider third party opinion.
21 | Construction | DNO/IDNO budget costs being exceeded by actuals. | x | x |  |  | 4 | 3 | 12 | WVT | Chase actuals/review scope.

## Template
Risk ID | Risk Title | Risk Description | Causes | Impacts | Proximity Date | Risk Owner | Last Modified by | Date Modified | Impact | Probability | RAG Rating | Risk Tolerance | Controls | mitigations | Status | Action Taken
[5 empty] | date when risk should either be resolved or becomes an issue |  |  |  | H/M/L | H/M/L | Impact x Probability | What is the business happy to accept risk RAG rating wise | what is in place already | What needs to be done differently/new | Open/Closed/Issue | Comments on the risk etc
| Timelines | Procurement timelines for land purchase - November 23
| Radiology lead times | Radiology lead times are higher due to CDC programmes (Phillips 12mths, Canon 6mths)
| Western Power | Lead times noted as a National CDC programme risk
| Gas Main | Large high pressure has main to the right of the site. 15m clearance to be considered in the design
| Access Road | 3rd party ownership of access road, potential for additional legal/maintenance agreements