## 2023 Estimate Overall Capital
Appendix A
Budget
INTEGRATED ENERGY SOLUTIONS | BUDGET 27112023 |  | Revised Budget 18.5.20 |  |  |  | Revised Budget 21.7.20 |  |  |  | Revised Budget 23.9.20 |  |  |  | Revised Budget 9.10.20 |  |  |  | Revised Budget 20.10.20 (cost report 8) |  |  |  | Revised Budget 23.12.20 (cost report 10) |  |  |  |  | Revised Budget (add date) |  |  |  |  | Actual expenditure 2019/20 | [11 empty] | Actuals 20/21 | [11 empty] | Forecast 24/25 | [11 empty] | Actual 23/24 | Actual to MTh 10 + Forecast 24/25 | Forecast 25/24 | Total Forecast | Variance - Forecast v's Revised Budget 20.10.20 | Variance - Forecast v's Initial Budget | AECOM cost report no 12 | Variance to MTX Cost report
|  | Cross check | Total Capital | 19/20 | 20/21 | 21/22 | Total Capital | 19/20 | 20/21 | 21/22 | Total Capital | 19/20 | 20/21 | 21/22 | Total Capital | 19/20 | 20/21 | 21/22 | Total Capital | 19/20 | 20/21 | 21/22 | Total Capital | 19/20 | 20/21 | 21/22 | Diff | Total Capital | 23/24 | 24/25 | 25/26 | Diff | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
Construction Costs
Construction Costs - Centrica | 16555183.72 |  | 11902304 |  | 11902304 |  | 12038060 | 579283 | 11458777 |  | 12034581 | 579283 | 11455298 |  | 12034581 | 579283 | 11455298 |  | 12594581 | 579283 | 12015298 |  | 12667548 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -12667548 | -16555183.72 | 12601322 | -12601322
Works cost contingency from cost plan is omitted and an overall contingency included below | 0
Construction Costs - WVT - Shielding to Energy centre As Cost Plan | 0 |  | 1638106 |  | 1638106 |  | 1638106 |  | 1488164 | 149942 | 1638106 |  | 1488164 | 149942 | 1638106 |  | 1488164 | 149942 | 1638106 |  | 1488164 | 149942 | 844942 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2020-09-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0; 2024-05-01: 0; 2024-06-01: 0; 2024-07-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | -844942 | 0 | 844942 | -844942
Construction/Enabling costs - Sodexo/MHL | 0 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 2024-03-01: 0; 2024-04-01: 0; 2024-05-01: 0; 2024-06-01: 0; 2024-07-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1171875 | -1171875
Total Construction Costs | 16555183.72 | #REF! | 13540410 | 0 | 13540410 | 0 | 13676166 | 579283 | 12946941 | 149942 | 13672687 | 579283 | 12943462 | 149942 | 13672687 | 579283 | 12943462 | 149942 | 14232687 | 579283 | 13503462 | 149942 | 13512490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13512490 | -16555183.72 | 14618139 | -14618139
Trust Professional Fees
Mercia & Sodexo PFI CN's. | 216000 |  | 120150 | 6422 | 113728 |  | 120150 | 6422 | 113728 |  | 120150 | 6422 | 113728 |  | 120150 | 6422 | 113728 |  | 120150 | 6422 | 113728 |  | 120150 | 6422 | 102356.6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-03-01: 6422; 2020-04-01: 11373; 2020-05-01: 21131; 2020-06-01: 1615; 2020-07-01: 11373; 2020-08-01: 11373; 2020-09-01: 11373; 2020-10-01: 11372.8; 2020-11-01: 11373; 2020-12-01: 5686.4; 2024-01-01: 5686.4; 2024-02-01: 0; 2024-03-01: 0 | [5 empty] | 6422 | 102356.6 | 0 | 108778.6 | -11371.4 | -107221.4
Trust Lawyers - Estimate | 15000 |  | 11500 | 4728 | 6772 |  | 11500 | 4728 | 6772 |  | 11500 | 4728 | 6772 |  | 11500 | 4728 | 6772 |  | 11500 | 4728 | 6772 |  | 11500 | 4728 | -109 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-03-01: 4728; 2020-11-01: -1288; 2024-02-01: 1179; 2024-03-01: 0 | [5 empty] | 4728 | -109 | 0 | 4619 | -6881 | -10381
Design Costs - Centrica | 0 |  | 28815 | 28815 |  |  | 28815 | 28815 |  |  | 28815 | 28815 |  |  | 28815 | 28815 |  |  | 28815 | 28815 |  |  | 28815 | 28815 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-03-01: 28815 | [5 empty] | 28815 | 0 | 0 | 28815 | 0 | #REF!
Structural & Civil Eng. Design Centrica | 0
MEP Design Centrica | 0
Cost Consultant Centrica | 0
Fire Engineer Centrica | 0
Acoustic Eng. Centrica | 0
Transport Consultant NIL | 0
Pre Demolition Audit NIL | 0
NEC Project Manager and Supervisor N/A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0 | 0 | 0 | 0 | -55000 | 0
WVT Project Manager - 2 years | 180000 |  | 265148 | 93380 | 93240 | 78528 | 265148 | 93380 | 93240 | 78528 | 265148 | 93380 | 93240 | 78528 | 265148 | 93380 | 93240 | 78528 | 265148 | 93380 | 93240 | 78528 | 265148 | 93380 | 85448 | 0 |  | 0 | 0 | 0 | 0 | 0 | [11 empty] | 93380 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93380 | 85448 | 0 | 178828 | -86320 | -1172
Project Support - not included | 0 |  | 123540 | 5389 | 94451 | 23700 | 123540 | 5389 | 94451 | 23700 | 123540 | 5389 | 94451 | 23700 | 121972 | 5389 | 92883 | 23700 | 121972 | 5389 | 92883 | 23700 | 109000 | 5388 | 73278 | 0 |  | 0 | 0 | 0 | 0 | 0 | [11 empty] | 5388 | 4859 | 3946 | 4654 | 12010 | 8014 | 7979 | 7978 | 7973 | 3946 | 3946 | 7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5388 | 73278 | 0 | 78666 | -30334 | 78666
Finance VAT advisor only District Val TBC | 0 |  | 15000 |  | 10000 | 5000 | 15000 |  | 10000 | 5000 | 15000 |  | 10000 | 5000 | 15000 |  | 10000 | 5000 | 15000 |  | 10000 | 5000 | 15000 | 0 | 4000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2020-09-01: 4000; 2024-04-01: 0; 2024-05-01: 0; 2024-07-01: 0 | [5 empty] | 0 | 4000 | 0 | 4000 | -11000 | 4000
Internal financial support NIL | 0 |  | 58145 | 3547 | 30598 | 24000 | 55211 | 3547 | 27664 | 24000 | 55211 | 3547 | 27664 | 24000 | 55087 | 3547 | 27540 | 24000 | 55087 | 3547 | 27540 | 24000 | 80000 | 3547 | 25543 | 0 |  | 0 | 0 | 0 | 0 | 0 | [11 empty] | 3547 |  | 1701 | 2559 | 2559 | 2559 | 2559 | 2559 | 2559 | 3242 | 2687 | 2559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 25543 | 0 | 29090 | -50910 | 29090
Project support from Sodexo CN | 0 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-02-01: 0; 2024-03-01: 0 | [5 empty] | 0 | 0 | 0 | 0 | -50000 | 0
BREEAM Assessor N/A | 0 |  | 17451 | 2435 | 15016 |  | 17451 | 2435 | 15016 |  | 17451 | 2435 | 15016 |  | 17451 | 2435 | 15016 |  | 17451 | 2435 | 15016 |  | 17000 | 2435 | 5400 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-03-01: 2435; 2020-05-01: 3600; 2020-07-01: 1800; 2020-11-01: 0; 2020-12-01: 0; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0 | [5 empty] | 2435 | 5400 | 0 | 7835 | -9165 | 7835
Life Cycle Plan (included in CN's) | 0 | [13 empty] | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Non Estates project support | 0 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 54000 |  | 40000 | 0 | 7541.5611 | 12000 |  | 0 | 0 | 0 | 0 | 0 | 2020-04-01: 2269; 2020-06-01: 8413; 2020-07-01: 4813.1111; 2020-08-01: -5213; 2020-09-01: 6245; 2020-10-01: 6245; 2020-11-01: 8317.45; 2020-12-01: 6245; 2024-01-01: 6245; 2024-02-01: -36038; 2024-03-01: 0; 2024-05-01: 4000; 2024-06-01: 4000; 2024-07-01: 4000; 2024-08-01: 0 | [5 empty] | 0 | 7541.5611 | 12000 | 19541.5611 | -20458.4389 | 19541.5611
Decant/removals | 0 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 |  | 30000 | 0 | 0 | 30000 |  | 0 | 0 | 0 | 0 | 0 | 2024-04-01: 10000; 2024-05-01: 10000; 2024-06-01: 10000 | [5 empty] | 0 | 0 | 30000 | 30000 | 0 | 30000
Engineering Support for estates check and challenge - budget | 60000 |  | 0 |  |  |  | 51000 |  | 51000 |  | 52000 |  | 52000 |  | 52000 |  | 52000 |  | 52000 |  | 52000 |  | 0 | 0 | 43576 | 12000 |  | 0 | 0 | 0 | 0 | 0 | 2020-06-01: 3733; 2020-09-01: 4242; 2020-11-01: 0; 2020-12-01: 6662; 2024-01-01: 0; 2024-02-01: 13323; 2024-03-01: 15616; 2024-05-01: 6000; 2024-06-01: 6000 | [5 empty] | 0 | 43576 | 12000 | 55576 | 55576 | -4424
Miscellaneous Fees at 5% - Will be transferred to costed Risk Register | 23550 |  | 0 |  |  |  | 789 |  | 789 |  | 4089 |  | 4089 |  | 4089 |  | 4089 |  | 4089 |  | 4089 |  | 0 | 0 | 3358 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2020-06-01: 789; 2020-07-01: 3300; 2020-11-01: -756; 2024-03-01: 25 | [5 empty] | 0 | 3358 | 0 | 3358 | 3358 | -20192
Sub-total | 494550 | #REF! | 773749 | 144716 | 497805 | 131228 | 822604 | 144716 | 546660 | 131228 | 826904 | 144716 | 550960 | 131228 | 835212 | 144716 | 559268 | 131228 | 835212 | 144716 | 559268 | 131228 | 838509 | 144715 | 350392.1611 | 54000 | 289401.8389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144715 | 26269 | 38146 | 29531 | 43623.1111 | 24501 | 44166 | 35922.8 | 35946.45 | 33549.4 | 26332.4 | -3236 | 15641 | 10000 | 20000 | 20000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144715 | 350392.1611 | 54000 | 549107.1611 | -272505.8389 | #REF! | 1250991 | -701883.8389
Project Resilience
Resilience capital cost | 605942.07
Resilience fund. | 769943.15
Sub-total | -164001.08
Equipment | [26 empty] | 0
N/A | 0 | #REF! | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 |  | 860685 | 0 | 562854.46 | 100000 | 197830.54 | 0 | 0 | 0 | 0 | 0 | 2020-09-01: 15126; 2020-10-01: 33313; 2020-11-01: 35338; 2020-12-01: 172595; 2024-01-01: 95646; 2024-02-01: 102399; 2024-03-01: 108437.46; 2024-04-01: 100000 | [5 empty] | 0 | 562854.46 | 100000 | 662854.46 | -197830.54 | 662854.46 | 860685 | -197830.54
Total Equipment | 0 | #REF! | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 860685 | 0 | 562854.46 | 100000 | 197830.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15126 | 33313 | 35338 | 172595 | 95646 | 102399 | 108437.46 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562854.46 | 100000 | 662854.46 | -197830.54 | 662854.46 | 860685 | -197830.54
0
Contingency | [21 empty] | 355467 |  |  |  |  | 0
Projected Contingency | 203440.602 | #REF! | 1141941 |  | 1141941 |  | 963685 |  | 963685 |  | 967164 |  | 967164 |  | 967164 |  | 967164 |  | 407164 |  | 407164 |  | 51697 | 0 | 0 | 0 | 51697 | 0 | 0 | 0 | 0 | 0 | 2024-04-01: 0 | [5 empty] | 0 | 0 | 0 | 0 | -51697 | -203440.602 | 879500 | -879500
Sub-total | 203440.602 | #REF! | 1141941 | 0 | 1141941 | 0 | 963685 | 0 | 963685 | 0 | 967164 | 0 | 967164 | 0 | 967164 | 0 | 967164 | 0 | 407164 | 0 | 407164 | 0 | 51697 | 0 | 0 | 0 | 51697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51697 | -203440.602 | 879500 | -879500
[27 empty] | 0 |  |  |  |  | 0
Inflation advice required assume % - FIXED COST | 0 | #REF! | 203107 |  | 203107 |  | 203107 |  | 131792 | 71315 | 203107 |  | 131792 | 71315 | 203107 |  | 131792 | 71315 | 203107 |  | 131792 | 71315 | 203107 | 0 | 0 | 0 | 203107 | 0 | 0 | 0 | 0 | 0 | 2024-04-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -203107 | 0 | 203107 | -203107
[27 empty] | 0 | 0 |  |  |  | 0
VAT | 3377146.528 | #REF! | 3389065 |  | 3389065 |  | 3380565 | 59451 | 3276863 | 44251 | 3380565 | 59451 | 3276863 | 44251 | 3380565 | 59451 | 3276863 | 44251 | 3380565 | 59451 | 3276863 | 44251 | 3389065 | 59451 | 3267616 | 53498 | 8500 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 59451 | 67382.915 | 0 | 175985 | 319357 | 271842 | 196750 | 257947.24 | 103842 | 181532 | 165043 | 198998 | 161887.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53498 | 59451 | 2100566.8503 | 53498 | 2213515.8503 | -1175549.1497 | -1163630.6777 | 3389065 | -1175549.1497
VAT Recovery estimate | -269342.77 | bar: 2024-04-01
TOTAL ESTIMATED PROJECT COST | 19993536.398
Salix Grant | 20196977
Difference. | 203440.602 | [25 empty] | 0 |  |  |  |  | 0
|  |  | 21938291 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0
[71 empty] | Total Contingency | 0
[71 empty] | Contingency required | #REF!
[71 empty] | Difference | #REF!
Note on O7: Chambers, Rae: Cost Report No 7 23.9.20
Note on T7: Chambers, Rae: Cost Report No 7 23.9.20
Note on X7: Chambers, Rae: Cost Report No 7 23.9.20
Note on AC7: Ingman, Josh: Less £325,000 which is for the new corridor (line 43)
Note on AZ7: Roden, Heather: Less VAT shown on VAT line
Note on BD7: Chambers, Rae: 14.8.20 - Commitment is too little by £130,962 as reversal of last months retention commitment not taken into account
Note on BH7: Ingman, Josh: HR contacted AECOM for details of 2mil less HR to speak with Kate.
Note on BI7: Ingman, Josh: Forecast £800,731
Note on CC7: Ingman, Josh: On the forecast this is down for Apr 22. Ask HR to review.
Note on AC9: Ingman, Josh: £793164 used to fund corridor, from construction risk allowance
Note on BE9: Chambers, Rae: GV 24.6.20 estimate had April
Note on BK9: Ingman, Josh: £116,850 expected to be done in Jan & Feb. Has this work been undertaken, does this need to be accrued? Do we have details of work complete and invoices?
Note on BK15: Ingman, Josh: Accrual input for April-Jan. Need details of this for year end. Will likely need to increase accrual for Feb & Mar 21.Need to check with Graham.
Note on BK16: Ingman, Josh: Capsticks accrual of £5534 should have been reduced to reflect these costs of £1179. Reduce in M12. All on C0100065155001.
Note on BA27: Chambers, Raemon: S Watkins 3,946 Webcam & cable £64 Docking station £254 It Equipment £595
Note on BB27: Chambers, Raemon: S Watkins 3,946
Note on BC27: Chambers, Raemon: S Watkins 3,946 Print 3 Tv 705
Note on BD27: Chambers, Raemon: S Watkins 3,946 K Nation 8,054 Print 10
Note on BE27: Chambers, Raemon: S Watkins 3,946 K Nation 4,027 Print 41
Note on BF27: Chambers, Raemon: S Watkins 3,946 K Nation 4,027 Print 6
Note on BI27: Ingman, Josh: No charge for KM Nation
Note on BJ27: Ingman, Josh: No charge for KM Nation
Note on BL27: Ingman, Josh: Includes Dec & Jan recharge for KM Nation
Note on BD29: Chambers, Rae: £1,159 added to contingency
Note on BE29: Chambers, Rae: £227 added to contingency £41 added to contingency
Note on BF29: Chambers, Rae: £227 added to contingency
Note on BG29: Chambers, Rae: £227 added to contingency
Note on BH29: Chambers, Rae: £227 added to contingency
Note on BI29: Chambers, Rae: £227 added to contingency
Note on BJ29: Chambers, Rae: £227 added to contingency
Note on BK29: Chambers, Rae: £227 added to contingency
Note on BL29: Chambers, Rae: £227 added to contingency
Note on BK30: Ingman, Josh: £25000 was forecast in Feb - was any work undertaken - should this be accrued for? Pushed all back in to March whilst details are being checked
Note on BH31: Ingman, Josh: No charge but had a forecast of £3,196
Note on BI31: Ingman, Josh: No costs so forecast pushed back
Note on BJ31: Ingman, Josh: No costs so forecast pushed back
Note on BK31: Ingman, Josh: No costs so forecast pushed back. Are costs expected this FY. Has work been undertaken should this be being accrued?
Note on BJ32: Ingman, Josh: No costs so forecast pushed back
Note on BK32: Ingman, Josh: No costs so forecast pushed back. Are costs expected this FY. Has work been undertaken should this be being accrued?
Note on BK33: Ingman, Josh: Dropped accruals for Midland Endocrine & Osteoporosis as currently no evidence to back up accrual as based on forecast. Need to check with Graham if any work has been undertaken by Clinician/nurse for project support since August.
Note on BH35: Ingman, Josh: 0 rather than 8805, is this due to the delay in opening?
Note on BK35: Ingman, Josh: Invoiced up to end of December. Has work been undertaken for Jan-Mar, if so work will need to be accrued for. Check with Graham.
Note on BN35: Roden, Heather: £12k for commissioning
Note on BC36: Chambers, Rae: Contingency reduced by this Environ Management - £789 - soil sampling
Note on BD36: Chambers, Rae: Contingency reduced by this Integrated Transport Planning - £3,300 - transport plan
Note on BL36: Ingman, Josh: Pull print costs
Note on AC37: Ingman, Josh: Report + £16,896 funded from contingency (reduced on line 43)
Note on AI37: Ingman, Josh: Report + £16,896 funded from contingency (reduced on line 43)
Note on BH45: Ingman, Josh: Significantly less due to delay from Jan/Feb opening to April - £35k rather than 270k forecast
Note on C54: Burke, Peter: No VAT on contingency
Note on L54: Chambers, Rae: 21.7.20 - Reduced by £8,500 being VAT included in £51k fee increase
Note on Q54: Chambers, Rae: 21.7.20 - Reduced by £8,500 being VAT included in £51k fee increase
Note on V54: Chambers, Rae: 21.7.20 - Reduced by £8,500 being VAT included in £51k fee increase
Note on Z54: Chambers, Rae: 21.7.20 - Reduced by £8,500 being VAT included in £51k fee increase
Note on AC54: Ingman, Josh: May need to be reduced by £8,500 as per Rae's comments from 21.07.20 regarding £51k fees
Note on AE54: Chambers, Rae: 21.7.20 - Reduced by £8,500 being VAT included in £51k fee increase
Note on AZ54: Roden, Heather: 59451 MTX VAT on works not design
Note on BI54: Chambers, Rae: 21.7.20 - reduced by £49,008 to balance -20% of R9+R37+R42+R44 is greater than R46 18.9.20 increased by £26,192 to balance

## Centrica CSA
IES
Centrica CSA
Item | Sum | C/f to 2023 Estimate Overall Capital
Project Approval | 355000 |  | 355000
Out to tender | 269842.5 |  | 269842.5
Tenders returned | 472485.83 |  | 472485.83
3694180
Order Placed | 3694180 |  | 177522.5
88761.25
Designs Completed | 355045 |  | 88761.25
22260
Insurance | 22260 |  | 163090
Signature of Agreement | 163090 |  | 35550
Welfare Cabins Physically on site | 35550 |  | 6000
Cavity Wall Insulation | 6000 |  | 20806
| 20806 |  | 2033
Loft Insulation | 2033 |  | 8700
| 8700 |  | 1844390.55
Heat Pumps | 1844390.55 |  | 1844390.55
| 1844390.55 |  | 1844390.55
| 1844390.55 |  | 1541636.3
| 1541636.3 |  | 1541636.3
| 1541636.3 |  | 1541636.3
| 1541006.3 |  | 68150
Autoclaves | 68150 |  | 68150
| 68150 |  | 68150
| 68150 |  | 49370
-50000
Helga | 49370
Completed on site | 249910 |  | 249910
154670.28
Final commissioning | 154670.28 |  | 154670.28
| 154670.28 |  | 154670.28
| 154670.28 |  | 150000
150000
Unallocated | 25000 |  | 150000
Contingency |  | see summary page
see summary page
see summary page
Sub-total | 16555183.72 |  | 16930813.72
16930814
| 3311036.744 |  | 0.28
19866220.464

## PFI CN's
Number | Detail | Detail | ESH Cost | IES Cost
2784 | Acknowledgement and Agreement | 1. Acknowledgement and agreement to locate and install IES infrastructure and equipment within Mercia Healthcare Ltd liability areas and boundaries 2. This scheme seeks to reduce the Wye Valley NHS Trust carbon footprint, where associated infrastructure and equipment, including service(s) delivery will be treated as Trust Capped Estate and obligation, unless otherwise stipulated explicitly through CCNxxF. | 1000 | 1000
2784c | Lender Notification and Fees | As part of the construction of the IES Scheme Phase 2 PSDS3, and in accordance with the Deed of Indemnity, the Trust request the following from Mercia Healthcare Ltd: 1. Collate project detail, raising Lender notification and associated fees for Lender and Lender TA review and; 2. Mercia Healthcare Ltd to address any Lender requirements, queries, in order to satisfy Lender review and with regard to the project generally. | 10000 | 10000
2784d | Legal and Professional Fees | As part of the construction of the IES Scheme Phase 2 PSDS 3, and in accordance with the Deed of Indemnity, the Trust request the following from Mercia Healthcare Ltd: 1. Collate project detail, raising legal notification and associated fees for Legal and any Legal review and; 2. Legal and Professional fees associated with capturing changes to the project documents and associated management requirements. | 10000 | 15000 | 5750 | 2804d As part of the construction of the IES Scheme Phase 2 PSDS 3, and in accordance with the Deed of Indemnity, the Trust request the following from Mercia Healthcare Ltd: 1. Collate project detail, raising legal notification and associated fees for Legal and any Legal review and; 2. Legal and Professional fees associated with capturing changes to the project documents and associated management requirements. SPC Commentary - This Variation Submission Return is a shared budget (£5,000) between FM & Project Co., where all costs allocated will be demonstrated via fee proposals and associated invoices received by each respective party. FM & Project Co. DEL costs will also be allocated, on our agreed schedule of rates (2023-2024) basis.
2784e | Deed of Indemnity Acknowledgement (PA) | 1. The Trust request access to construct, pursuant to the IES Scheme Phase 2 PSDS 3 and in accordance with the terms within the ‘Deed of Indemnity'. ‘In accordance with Clause 21.4 of the PA, the purpose of this CCN is to ascertain and deal with any consequences upon the rights, obligations, risks, responsibilities and entitlements of the Company under the Total Contract and/or the Facilities and/or the Services of and prior to the undertaking and performance of the Outsourced Services that are to be undertaken and/or performed by the Trust and/or the Third Party Supplier as appropriate’. 2. The Trust recognises that preparation of a Deed of Indemnity is in hand and that this Deed of Indemnity will ascertain and deal with any consequences upon the rights, obligations, risks, responsibilities and entitlements of the Company under the Total Contract and/or the Facilities and/or the Services of and prior to the undertaking and performance of the Outsourced Services that are to be undertaken and/or performed by the Trust and/or the Third Party Supplier as appropriate but until this Deed of Indemnity is finalised and executed, Clause 21.5 shall apply’.
2784f | Deed of Indemnity Drafting, Review and Finalising | As part of the construction, pursuant to the IES Scheme Phase 2 PSDS 3, and in accordance with the Deed of Indemnity acknowledgment (CCN 27xxC) the Trust request the following from Mercia Healthcare Ltd: 1. Collate known project (PA) and IES detail, then templating, drafting, reviewing and finalising the associated Deed of Indemnity. | 10000 | 10000 | 28750 | 2804b As part of the construction, pursuant to the IES Scheme Phase 2 PSDS 3, and in accordance with the Deed of Indemnity acknowledgment (CCN 2804C) the Trust request the following from Mercia Healthcare Ltd: 1. Collate known project (PA) and IES detail, then templating, drafting, reviewing and finalising the associated Deed of Indemnity. SPC Commentary - This Variation Submission Return is a shared budget (£25,000) between FM & Project Co., where all costs allocated will be demonstrated via fee proposals and associated invoices received by each respective party. | This CN now includes the surplus from 2804D see email RE: CCN WVT Approval 2804b - IES PSDS 3 Legal and Professional Fees (SPC Response)
2784g | Deed of Rectification Drafting, Review and Finalising | As part of the construction, pursuant to the IES Scheme Phase 2 PSDS 3, and in accordance with the Deed of Indemnity (CCN 27xxD) the Trust request the following from Mercia Healthcare Ltd: 1. Collate known project (PA) and IES detail, then templating, drafting, reviewing, finalising and completing the associated Deed of Rectification. | 10000 | 10000 | 10000 | 2804e
2784h | Deed of Variation Drafting, Review and Finalising | As part of the construction of the IES Scheme Phase 2 PSDS 3, and in accordance with the Deed of Indemnity and Deed of Rectification, if so required (CCN 27xxD & 27xxE), the Trust request the following from Mercia Healthcare Ltd: 1. Collate known project (PA) and IES detail, then templating, drafting, reviewing, finalising and completing the associated Deed of Variation. | 10000 | 10000 | 10000 | 2804f Deed of variation drafting
2784i | Project and FM Co Technical Support and Attendance | The Trust require the support of Mercia Healthcare Ltd and Sodexo to develop the project including such services as commenting on the design, then with Sodexo only, carrying out/overseeing site surveys/investigations, inductions, checking RAMS and managing access to the site on behalf of the Trust. This is not exhaustive and will be instructed as required by the Trusts Project Manager or delegate in liaison with Mercia Healthcare Ltd and Sodexo as appropriate. This is an open CCN to be charged by way of part completion certificates on an open book basis between the Sodexo lead and Trust Project Manager. For clarity the above does not include management of the Trust main contractor or their subcontractors. The requirement is solely for support and interaction with pre-construction services/activity. | 20000 | 30000 | 50000 | 2804 g The Trust require the support of Mercia Healthcare Ltd and Sodexo to develop the project including such services as commenting on the design, then with Sodexo only, carrying out/overseeing site surveys/investigations, inductions, checking RAMS and managing access to the site on behalf of the Trust. This is not exhaustive and will be instructed as required by the Trusts Project Manager or delegate in liaison with Mercia Healthcare Ltd and Sodexo as appropriate. This is an open CCN to be charged by way of part completion certificates on an open book basis between the Sodexo lead and Trust Project Manager. For clarity the above does not include management of the Trust main contractor or their subcontractors. The requirement is solely for support and interaction with pre-construction services/activity. SPC Commentary - This Variation Submission Return is a shared budget (£50,000) between FM & Project Co., where all costs allocated will be demonstrated via fee proposals and associated invoices received by each respective party.
2784j | Project Co CDM_A Support and Attendance | To support the Trust, as well as confirming adequacy to Trust provisions discharged via their consultants, sub-contractors and other organisations, Mercia Healthcare Ltd. require CDM-A provisions for the duration of the project, inclusive of, but not limited to; Discharging of all Client responsibilities from MHL-WVT Review of all Pre-Construction information Review of all Health & Safety information Periodic site visits, site project review and associated report collation Review of Trust discharged responsibilities to PD & PC throughout | 5000 | 15000
2784k | Project Co Project Management and Representation | To support the Trust adequately, for the duration of the project, Mercia Healthcare Ltd require additional support to enact Project Co. representation, for the duration of the ESH Project, where required and inclusive, but not limited to; Review Trust contractor design, construction, services and progress reports Attend and chair Variation Quality Review (VQC) Committee Meetings (Semperian Internal) Attend, where in leiu of the SPC and/or ASPC Manager, ESH Project Meetings Assisting with any DoI, DoR and DoV collation of information, where in leiu of the SPC Manager Generally, at the discretion of both the Trust and Project Co. but where only agreed by both parties | 15000 | 80000
2784l | Project Co Construction Insurances | To support the Trust adequately, for the duration of the project, where construction and H&S Risk is concerned. Mercia Healthcare Ltd are required to advise, raise and seek insurance premium costs for the project programme, until such a time practical completion has been arrived. Full site project insurances will not included, where update to existing annual insurance reinstatement will not be covered under this CCN request | 5000 | 15000
2784m | Mercia Healthcare Ltd General and Infrastructure Services Support | The Trust require the support of Mercia Healthcare Ltd for all required internal and external costs associated with general, infrastructure and direct service connections support to the IES Scheme Phase 2 PSDS 3. | 5000 | 20000 | 20000 | 2804k
216000

## Future works
Cost estimate for increasing works scope to add MRU & SRU | 240000

## Boiler LCC
Lifecycle (From Trust) | 450000

## Sheet1
Resilience Options costs.
The table below seeks to identify the resilience options costs.
| Caital investment. | Per annum | 10 year period | Total
Option 1 | -5000000 |  |  | -5000000
Option 2 | 0 | -500000 | -5000000 | -5000000
Option 3 | -1412468.03 | 20000 | 200000 | -1212468.03
Option 4 | 164001.08 | -10000 | -100000 | 64001.08
Note:
Option 3's technology enables the future works costs for increasing the PSDS scope to include the MRU and SRU to reduce from 230K to 50K.
Per annum = On-going yearly cost/saving outside of CBS yeraly maintenance charges.

## Reslience Options costs
IES Heating resilience options |  | 2023-11-14
Option 1 - New Electrode Back up Generators. |  |  |  | Option 2 - Retain the existing Gas steam boilers
This option is to install new standby electric generators which would supply the Energy Centre with electricity in the event of a loss of power to site. |  |  |  | Requirement to run steam boilers in hot standby
Budget cost at 5m and very large space to site equipment, this option discounted. |  |  |  | Budget cost per annum |  | -500000
|  |  |  | Centrica costs |  | 552550
|  |  |  | LCC contribution |  | -450000
Option 3 - DNO Dual supplies |  |  |  | Option 4 - Steam Boiler Plant replacement
NGED Non - contestable works | 494958.65 |  | 441647.03 | Centrica cost |  | 605942.07
Contestable works - civils & cable install
ESM - MP03761 Rev 2 | 2112663.04 |  | 3391991
EAST - Q9063 - Rev 1 | 4774550.7 |  | 4959888.7
Sum of NGED and ESM charges |  |  | 3833638.03
CBS Provision |  |  | 1868620
Difference. |  |  | -1965018.03 |  |  | 605942.07
LCC contribution |  |  | 552550 | LCC contribution |  | 552550
Savings from LCC/Maintenance/Standing charges/- pa |  |  | 20000 | Funds made available from single DNO (this option) being under budget - see table below. |  | 217393.15
769943.15
Difference |  |  | -1412468.03 |  |  | 164001.08
Supply from one S/S assisting with contributing funds to option 4
|  |  |  | NGED Non - contestable works | 494958.65 | 441647.03
Contestable works - civils & cable install
|  |  |  | ESM - budget |  | 1209579.82
|  |  |  | EAST - budget |  | 1698217.95
1651226.85
|  |  |  | CBS Provision |  | 1868620
217393.15
|  |  |  | LCC contribution |  | 552550
|  |  |  | Difference |  | 769943.15
|  |  |  | Centrica cost |  | 605942.07
|  |  |  | Difference |  | 164001.08
Note on O13: Burke, Peter: zero?
Note on G34: Burke, Peter: will increase to @512K is the 450K net of VAT?
Note on O34: Burke, Peter: will increase to @512K is the 450K net of VAT?
Note on G35: Burke, Peter: estimate
Note on O58: Burke, Peter: will increase to @512K is the 450K net of VAT?